## Requirements Stack
Requirement ID | Description | Story Points | Priority | Sprint No. (tentative)
1 | User Registration: System allows users to create an account using an email and password. | 1 | 1 | 1
2 | User Login: System allows registered users to login using their credentials | 1 | 1 | 1
3 | Profile Management: Allows users to update profile information such as name, email, and password. | 5 | 2 | 2
4 | Trip Creation: System allows users to create a new trip by specifying a trip name, destination, and dates. | 2 | 1 | 1
5 | View Trip List: Allows users to view a list of all their created/planned trips | 2 | 1 | 1
6 | Delete Trip: Users are able to delete a trip from their account. | 2 | 3 | 2
7 | Google Maps Integration: The system shall display a map using Google Maps API, allowing users to search for locations and landmarks. | 3 | 2 | 3
8 | Add activity to Itinerary: users can add activities to their itinerary by selecting a location and entering activity details (name, time) | 3 | 1 | 1 ==> 2
9 | View Itinerary: users can view a day-by-day itinerary, showing scheduled activities | 3 | 2 | 2 ==> 1
10 | Edit Activity: users can edit activity details in the itinerary | 5 | 3 | 3
11 | Delete Activity: System allows users to delete/cancel an activity in the itinerary | 5 | 3 | 2
12 | Expense Log: users can log expenses under a trip and categorize them | 5 | 3 | 3
13 | View Expense Summary: user can view a summary of their expenses broken down by category | 8 | 3 | 3
14 | Export Itinerary: Users can export their entire trip itinerary and expenses as PDF | 8 | 4 | 4
15 | Share Trip: users can share their trip details with others via a link or email invite | 8 | 4 | 4
16 | User Collaboration: multiple users can collaborate on a trip and edit the itinerary | 13 | 4 | 4
17 | Security: system only allows authenticated users to access and modify shared trips | 5 | 2 | 4
18 | Responsiveness: system will have smooth UI experience with little to no lagging | 13 | 2 | 2
19 | Weather Display: Show current weather for the main destination on the trip page using a basic weather API. |  | 4 | 4
20 | Basic Budget Field: Add a single budget field to each trip, where users can manually input the total trip budget. | 5 | 4 | 3